## Change Order Log
CO # | Date | Description | Requested By | Status | Cost Impact | Schedule Impact | Days Requested | Days Approved | Submitted Date | Approved Date | Supporting RFI / Doc | Notes
CO-001 | 2026-09-12 | Foundation revision due to rock | Site Super | Pending | $4,500.00 | Critical Path | 3 |  | 2026-09-12 |  | RFI-004, Daily Report | Awaiting structural review